## Slide 1: QuantEx : Project Kick-Off Efficient Quantum Circuit Simulation on Exascale Systems January 2020

## Slide 2: Overview
Context PRACE 6IP WP8
Staffing
Timeline
Project management

## Slide 3: PRACE 6IP-WP8
Objectives:
  Deliver solutions in the form of high quality, transversal software that address challenges posed by the rapidly changing HPC pre-Exascale landscape to HPC users and scientific communities.
  Advance strategic projects, selected in a transparent and competitive process, that require a long-term and significant dedicated effort.
  Allow for disruptive approaches to modernize HPC software, leveraging of software technologies adopted, developed, and maintained by the big players in IT
10 Projects funded: Initial eight started mid 2019, final two January 2020
Key Performance Indicators (draft)
  Percentage of projects that release software
  Percentage of projects that run codes efficiently on pre exa-scale machines
  Percentage of projects that are adopted by scientists

## Slide 4: Staffing
Project is 22 months and 66 PM: 3 FTE (2 at ICHEC and 1 at LRZ)
Current estimates:
  January to March: 0.93 – 1.33 FTE
    ICHEC: Niall 60-80%, Lee 0-20% ~ 60-100%
    LRZ: Luigi 33%
  March onwards: 3 FTE
    ICHEC: Niall 60%, Lee 40%, New hire 100%
    LRZ: New hire 100%
Aim to make up 2-3 PM during busy times

## Slide 5: Timeline

## Slide 6: M01-M03 tasks
Identify simple use cases
  Scripts which generate circuit descriptions QASM
End to end prototype (write one to throw away)
Evaluate available software:
  ExaTensor
  TAL-SH
  CUTENSOR
  Qflex
  Itensor
  …

## Slide 7: Project Management
Gitlab for code and project management, central repository at ICHEC, mirror repository at LRZ and elsewhere as needed
Class C project created at ICHEC to get access to resources, test account at LRZ and will watch for access to pre exa-scale machines
Meeting every two weeks at initial project stages
Face to face meeting to be arranged for April/May
To arrange initial stakeholder/user meeting, suggestions for additional stakeholders welcome
Slack group (if possible to add external members)